Onchocerciasis Elimination in Nigeria: Programme History, Progress and Outlook

Technical briefing for the National Onchocerciasis Elimination Committee (NOEC)  •  DRAFT  •  2 September 2026

Source: WHO/ESPEN portal — Afro_Country_Oncho_data, Afro_IU_Oncho_Flag_data, Oncho_Country_Forecast (extracted 2 Sep 2026). Implementation unit = LGA (n = 774).

1. PROGRAMME HISTORY

Nigeria carries the largest onchocerciasis burden of any country worldwide. Control began under the Onchocerciasis Control Programme (OCP) and expanded nationally through community-directed treatment with ivermectin (CDTI) under APOC from the mid-1990s, with Mectizan® donated by Merck & Co. In 2012 the national goal shifted from morbidity control to interruption of transmission and elimination. The NOEC was established to adjudicate stop-MDA and surveillance decisions, and since 2016 ESPEN has served as the regional data platform through which Nigeria reports annually (JRF submitted every year 2014–2025).

The current frame comprises all 774 LGAs. Treatment history is deep but uneven: the median LGA has completed 19 rounds of MDA (maximum 28), and 421 LGAs (54%) have ≥15 rounds — the point at which stop-MDA assessment becomes plausible under WHO guidelines.

2. PROGRESS OVER TIME (ESPEN REPORTED DATA)

| Year | IUs requiring MDA | IUs treated | Persons treated | Prog. coverage | IUs eff. treated | IUs under PTS |
| --- | --- | --- | --- | --- | --- | --- |
| 2014 | 478 | 428 | 46.2 m | 66.3% | 162 | 9 |
| 2016 | 487 | 394 | 35.9 m | 89.3% | 331 | 0 |
| 2018 | 487 | 442 | 48.3 m | 88.3% | 404 | 0 |
| 2020 | 436 | 352 | 49.6 m | 105.1% | 330 | 44 |
| 2021 | 421 | 107 | 13.2 m | 101.2% | 105 | 61 |
| 2023 | 356 | 287 | 48.5 m | 102.0% | 254 | 128 |
| 2025 | 260 | 257 | 50.3 m | 100.1% | 255 | 209 |

PTS = post-treatment surveillance. 2021 (shaded) reflects the COVID-19 / insecurity disruption.

The direction of travel is strongly positive. LGAs still requiring MDA have fallen 46%, from 478 (2014) to 260 (2025), while LGAs moved into post-treatment surveillance rose from 9 to 209. Delivery quality has also improved: 255 of 257 treated LGAs achieved effective (≥65%) coverage in 2025, against 162 of 428 in 2014. As at the 2024 assessment round, 327 LGAs (42%) are flagged as having suspected transmission interrupted (297) or suppressed (30).

3. KEY CHALLENGES TO ELIMINATION

- Unclassified LGAs are the binding constraint. 153 LGAs (20%) have no confirmed oncho status: 115 are masked under LF ivermectin MDA and 38 still require Onchocerciasis Elimination Mapping (OEM). LF MDA cannot be stopped in those LGAs until oncho status is resolved, and they cannot enter a stop-MDA pathway.

- Coverage denominators are unreliable. Reported programme coverage exceeded 100% in 2020, 2021, 2022 (163.5%), 2024 (120.0%) and 2025, and epidemiological coverage reached 143.5% in 2025. Denominators drawn from projected census figures will not withstand scrutiny at stop-MDA adjudication.

- A large and growing untreated at-risk population. Population in endemic LGAs receiving no treatment rose from 6.7 m (2019) to 15.8 m (2023) to 35.4 m (2025) — concentrated in LGAs where MDA was not delivered or status is unknown.

- Fragility of delivery. The 2021 collapse to 107 treated LGAs and 13.2 m treatments took two cycles to recover, and 94 endemic LGAs recorded no MDA in 2024. Insecurity, funding gaps and CDD attrition remain live risks to round continuity.

- Assessment capacity, not treatment capacity, is now the bottleneck. 56 LGAs were pending impact assessment in 2024 and 17 in 2025; the pipeline of Ov16 serosurveys, entomology and pre-stop assessments must scale faster than MDA scales down.

4. FIVE-YEAR OUTLOOK, 2026–2030 (ESPEN FORECAST)

| Year | Endemic IUs | IUs on MDA | Pop. requiring PC | IUs under surveillance | Stop-MDA surveys |
| --- | --- | --- | --- | --- | --- |
| 2026 | 50 | 76 | 7.22 m | 432 | 17 |
| 2027 | 41 | 57 | 6.49 m | 441 | 12 |
| 2028 | 37 | 39 | 6.16 m | 445 | 0 |
| 2029 | 33 | 35 | 5.70 m | 449 | 0 |
| 2030 | 25 | 27 | 4.76 m | 457 | 0 |

ESPEN projects continued, orderly contraction: LGAs on MDA fall by 64% (76 → 27), the population requiring preventive chemotherapy falls by a third (7.2 m → 4.8 m), and LGAs under surveillance rise to 457 by 2030. A major surveillance wave is scheduled for 2027 (360 LGAs), with pre-stop-MDA assessments spread across the period (9, 4, 4, 8 and 11 LGAs respectively).

Two caveats the NOEC should note. First, the forecast holds 248 LGAs (32%) in “unknown” status unchanged through 2030 and schedules no mapping activity after 2023 — so it describes the trajectory of the known endemic frame only, not national elimination. Second, its baseline (44 non-endemic LGAs) diverges from Nigeria’s 2025 reported data (135), and should be re-based against the latest JRF before it is used for commodity forecasting.

Bottom line: on current trajectory Nigeria will have retired MDA in the large majority of its endemic LGAs by 2030, but will not be positioned to claim national elimination of transmission unless the 153 unclassified LGAs are mapped and adjudicated within the next two to three years. Recommended NOEC priorities: (i) fund and schedule OEM in the 38 unmapped LGAs; (ii) resolve oncho status in the 115 LF-masked LGAs; (iii) commission a denominator review before the 2027 stop-MDA round; (iv) protect assessment financing as MDA financing declines.

Prepared for NOEC discussion. Figures are as reported to WHO/ESPEN and have not been independently validated; coverage values >100% are reproduced as reported.